## Slide 1: TRAINING FOR TRAINERS COURSE AND ACTION PLAN
CALEDONIA CLUBHOUSE,
SCOTLAND

## Slide 2: ELECT TRAINING MOSAIC CLUBHOUSE, LONDON
The training took place in Mosaic Clubhouse, London from 23rd-27th March 2009.
Training colleagues included:
Alison, Caledonia Clubhouse, Scotland
Liz and Peter, Scotia Clubhouse, Scotland,
Suzzi and Gabby - Fountain House, Malmo, Sweden
Triste and Thorunn, Geyser Clubhouse, Iceland
Cecilia and Mikko, Finland
The training team from Mosaic Clubhouse and training base included Hilary, Neill, Bev, Peter, Lee, Calvin, Mike, Ebrahim, Kabuya, Karen and June. Ville Gronberg also co-hosted the training on behalf of the European Learning Communities for Training of People with Mental Illness (ELECT Project).

## Slide 3: TRAINING SCHEDULE
Day 1: Introduction to course, hopes and expectations. Why education? Relationships and education support. Free evening.
Day 2: Adult learning styles, explanation of action planning and disclosures. Board meeting in the evening.
Day 3: Visit to Lambeth College and Kingston College, individual action planning with training staff. Dinner at Carlshalton College.
Day 4: Evaluation of college visits. Tutor from Lambeth College. Clubhouse best practices for education.
Day 5: Evaluation of pilot course. Presentation of action plans to colleagues and the training team.

## Slide 4: CALEDONIA CLUBHOUSE ACTION PLAN
Current Situation: Caledonia Clubhouse has a rolling programme of in-house educational courses with tutors provided by Forth Valley College. We have identified a need to develop a clear and structured pathway for members to access local Community Learning centres or college. Appropriate supports will have to be put in place to allow members to progress ands move on from Clubhouse according to their needs.
Rationale: Building on the success of the in-house courses to enable members to further their vocational or educational goals outside the Clubhouse.
These goals are based on Standards 14: (Space) and 25: (Education). Completion date for the action plan – September 2009.

## Slide 5: CALEDONIA CLUBHOUSE EDUCATION ACTION PLAN
ACTION STEPS
1. To present the Action Plan to members and staff at the community meeting and gauge feedback from the plan. Take the plan to unit meetings to allow more members to be involved in the planning. Set up a working group to look at how to take the action plan forward.
IMPLEMENTATION DATE
The next community meeting on 2nd April 2009.
OUTCOME:
Action step completed

## Slide 6: CALEDONIA CLUBHOUSE EDUCATION ACTION PLAN
ACTION STEPS:
2. Look at the Clubhouse space to allow members to be able to study and look at existing classes to see how it impacts on the work-ordered day.
3. Separate education and employment meetings to give education the same focus as employment.
IMPLEMENTATION DATE:
Week beginning 6th April 2009.
Outcome: Move the class to the meeting room and use the laptops.
The employment and education meeting 2nd April 2009.
Outcome: Education meetings will happen every alternative Thursday.

## Slide 7: CALEDONIA CLUBHOUSE EDUCATION ACTION PLAN
ACTION STEPS:
4. Invite student support worker/advisor to an Employment and Education dinner .
5. Re-establish the College student advisor bi-monthly surgeries at the Clubhouse
IMPLEMENTATION DATE:
Invite to next Employment and Education dinner in April/May 2009.
Outcome: Student advisor attended our employment and education dinner in May 2009.
After the summer recess in September 2009.
Outcome: Advisor attended May dinner and happy to re-establish his bi-monthly surgeries.

## Slide 8: CALEDONIA CLUBHOUSE EDUCATION ACTION PLAN
ACTION STEPS:
6: Arrange to meet with the appropriate support services at the College or learning centres as well as doing the preparatory work within the establishments to find out where the support services are.
IMPLEMENTATION DATE:
In September once the College has started back.
Outcome: A visit to College has been arranged for June 10th before recess.

## Slide 9: CALEDONIA CLUBHOUSE ACTION PLAN CONCLUSIONS:
The staff and members of Caledonia Clubhouse have embraced this Action Plan which can be evidenced with the number of members who have put themselves forward to go and visit the College with the intention of signing up for a certified College course.
Two dates have been set for College visits, one for the Moving Forward course which looks at personal development, core skills and enterprise. The second visit is to be introduced to the College support workers, mentors and advisors and to look at the flexi-learning centre.

## Slide 10: CALEDONIA CLUBHOUSE ACTION PLAN CONCLUSIONS:
The computer course will move from the business and administration unit to the meeting room and the room will be set up using the laptops, allowing members to study and the unit to continue with everyday business without disturbing the class.
We have made contact with local community learning centres and display their posters advertising current classes available throughout Falkirk.

## Slide 11: CALEDONIA CLUBHOUSE CURRENT COURSES
In-house – Computers for the Terrified (8) members), starting August 2009. Royal Horticultural Society – certificated course (12) members), starting September 2009.
Community Education – European Computer Driving License (ECDL) - 4 members. Gentle Step course – 3 members
Forth Valley College courses – Moving Forward course – 3 members. Introduction to Care course – 2 members.